## WBS
Work Breakdown Structure — Pet Adoption & Shelter Management System (PS #57)
Effort figures are planning estimates in person-hours; status reflects the repository as of this version.
WBS ID | Level | Work Package | Deliverable | Traces To | Est. Effort (h) | Status
1 | 1 | Pet Adoption & Shelter Management System | Complete individual project | PS #57
1.1 | 2 | Project Management
1.1.1 | 3 | Project setup | GitHub repository, Jira Scrum and Kanban projects | 3-Project-Creation | 4 | Done
1.1.2 | 3 | Sprint planning and tracking | Epic, backlog, Sprint 1 with 7 FR/NFR items | 3-Project-Creation | 4 | Done
1.1.3 | 3 | Progress reporting | Board updates, sprint review notes | — | 3 | In progress
1.2 | 2 | Requirements Engineering
1.2.1 | 3 | Problem analysis | Actors, scope and stakeholder goals | PS #57 | 2 | Done
1.2.2 | 3 | Requirements table | FR-001 to FR-005, NFR-001, NFR-002 | 1-RE | 4 | Done
1.2.3 | 3 | Use-case diagram | UC-01 to UC-11 with «include» / «extend» | 7-UML-Diagrams | 3 | Done
1.2.4 | 3 | Use-case flow specification | UC-02 flow, alternate flow 4a, exception flows E1–E2 | 4-SRS-and-WBS | 3 | Done
1.2.5 | 3 | Traceability matrix | RTM: requirement ↔ use case ↔ planned test | 1-RE | 2 | Done
1.2.6 | 3 | SRS | IEEE 830-style specification | 4-SRS-and-WBS | 5 | Done
1.3 | 2 | Design
1.3.1 | 3 | Architecture design | Architecture diagram (client, server, database, email) | 2-Architectural-Diagram | 4 | Done
1.3.2 | 3 | Data and state model | Entities and animal / application lifecycles | SRS §6 | 3 | Done
1.3.3 | 3 | Activity modelling | Activity diagram for UC-02 | 7-UML-Diagrams | 2 | Done
1.3.4 | 3 | UI design | Wireframes: catalog, questionnaire, staff queue, foster list | SRS §7 | 4 | Pending
1.4 | 2 | Implementation
1.4.1 | 3 | Login and access control | Registration, login, role checks (401/403) | UC-10; NFR-002 | 8 | Pending
1.4.2 | 3 | Medical intake and quarantine | Intake records, quarantine flag, Ready status | UC-05, UC-11; FR-001 | 8 | Pending
1.4.3 | 3 | Catalog search and filter | Filtered catalog, public fields only | UC-01; FR-002, NFR-001 | 8 | Pending
1.4.4 | 3 | Adoption application | Questionnaire, validation, local draft, staff queue | UC-02; FR-003 | 10 | Pending
1.4.5 | 3 | Screening and decision workflow | Background checks, approve / reject / complete | UC-03, UC-04, UC-07, UC-09; FR-004 | 12 | Pending
1.4.6 | 3 | Notifications | Email and in-app status alerts | UC-08; FR-004 | 4 | Pending
1.4.7 | 3 | Foster placement management | Placements, overdue list, end placement | UC-06; FR-005 | 6 | Pending
1.4.8 | 3 | Copilot-assisted coding | Copilot screenshots / repository link | 5-GitHub-Copilot | 2 | Pending
1.5 | 2 | Testing
1.5.1 | 3 | Test planning | Test plan from RTM planned tests | RTM | 3 | Pending
1.5.2 | 3 | Functional testing | TC-FR001 to TC-FR005 | FR-001 to FR-005 | 8 | Pending
1.5.3 | 3 | Performance testing | TC-NFR001 load test (p95 < 200 ms) | NFR-001 | 3 | Pending
1.5.4 | 3 | Security testing | TC-NFR002 access-control tests | NFR-002 | 3 | Pending
1.5.5 | 3 | Bug tracking, fix and retest | Jira bug board, fixes, retest results | 6-Software-Testing | 6 | In progress
1.6 | 2 | Deployment and Closure
1.6.1 | 3 | Environment setup | Server, database, email configuration | — | 4 | Pending
1.6.2 | 3 | Deployment | Deployed portal and deployment steps | — | 3 | Pending
1.6.3 | 3 | Documentation | README and repository structure | README.md | 2 | In progress
1.6.4 | 3 | Demo | Demo video or output screenshots | — | 2 | Pending